## Slide 1: June 15-16, 2017 Steering Committee Meeting Summary of Conclusions and Action Items
Follow us: www.internationalhealthpartnership.net @UHC2030

## Slide 2
Work Plan Implementation
Need to increase visibility of UHC2030 at country level, and better define how global principles translate into action at the country level in terms of health systems strengthening coordination, advocacy, accountability and knowledge management
Need for clarity on how the work on advocacy, accountability and knowledge sharing builds on the different technical working groups’ work and ensure interlinkages
Need to communicate on how the different technical working groups function and relate to the Steering Committee, including opportunities for partners to engage
Work plan development process should be participatory, following procedures presented
EDC Monitoring & DAH Tracking
UHC2030 should focus on UHC, EDC is a subsect of this agenda and not parallel stream of work.
Conclusions

## Slide 3
Change how we define EDC in the SDG era, and do EDC monitoring working closely with OECD, GPEDC
UHC2030 to provide a safe space to discuss UHC issues to increase understanding and trust
Not a big appetite on expanding UHC2030 work on DAH tracking beyond this, but rather to promote broader work on data collection and management, looking at NHA, including domestic resource mobilization and external resources
Accountability
Need to articulate a UHC2030 accountability framework that integrates Global, Regional, National and Local Level efforts, as well as peer review mechanisms
An accountability report for the Dec 12 Tokyo meeting is over-ambitious. Others options such as a report focusing on selected countries already existing work could be explored.
Need to link/synergize UHC2030 initiatives with work of relevant regional initiatives
Conclusions (ctd)

## Slide 4
Advocacy, Communication and Knowledge Management
Need for clear, crisp and accessible messages and outputs that UHC2030 is aiming to achieve
Advocacy strategy should include all stakeholders, including citizens, and also focus on influencing political processes at the country level
SC supportive of the planned landscaping analysis as well as the emerging elements of the KM strategy
Knowledge management strategy should include possibilities for igniting/scaling up country level KM efforts and peer to peer learning.
UHC Forum
Strong support for UHC annual forum to take stock of UHC progress, knowledge sharing and as a means of facilitating global accountability.
As part of the annual/semi- annual fora, there is the need to have a sequence of themes that allows UHC2030 to track progress towards UHC achievement by 2030
Need to articulate UHC2030 links with other partnership and how UHC2030 is network of networks. Need to make space for different initiatives to access the Steering Committee as they contribute to country program implementation.
Conclusions (ctd)

## Slide 5
UHC2030 Ways of working
Need to articulate UHC2030 links with other partnership and how UHC2030 is network of networks. Need to make space for different initiatives to access the Steering Committee.
SC TORs
The SC should consider how best to engage the UN Special Envoy on UHC if and when he or she is appointed ( as stated in Dec background doc on governance)
Private Sector
Need for private sector in the platform is essential but there’s the need to manage the risks
Consider an ad hoc process for involving the private sector at the Steering Committee, pending finalization of TORs and conflict of interest policies. June 2018 will be a realistic timeline for full onboarding of the private sector.
Conclusions (ctd)

## Slide 6
Define framework for UHC2030 accountability: Set up a time bound expert group to work on accountability framework that includes options for global, regional, national, local and peer review efforts
Include in communication strategy how UHC2030 works, including how it relates to country implementation
Provide written overview of working groups and the process for joining the groups
Disseminate EDC monitoring results, including to the DAC and board of various institutions
Develop work plan for 2018-19
Finalize KM, Advocacy and Communications strategies by Dec 2017
Share a draft program for the UHC Forum with UHC2030 SC for inputs. Inputs to be consolidated by Core Team and shared Forum Steering Committee
SC members to submit to Core Team suggestions to strengthen the networks of networks proposition both at the strategic and operational levels.
Core Team to propose at next meeting pragmatic ways to foster operational collaboration, taking advantage of opportunities
Action Items – by December 2017

## Slide 7
PS Task Force and Core Team to finalize of TORs and conflict of interest policies.
Action Items – by December 2017